WATZS – Software Prototype Project Plan

Ananya & Guru | Python Backend + Web UI | ~4 Weeks | GitHub Collaboration

1. Team Module Split

Ananya — Audio Engine & AI Core

- Audio capture via PyAudio (laptop mic)

- Keyword detection using Vosk (offline speech-to-text)

- Abnormal sound classification using YAMNet (screams, gunshots, crashes)

- Secret emergency voice code logic

- Alert trigger/classifier that maps detections → alarm levels

Guru — Dashboard, Alerts & Backend

- Flask REST API (POST /alert, GET /events)

- Flask-SocketIO for real-time alert push to UI

- SQLite + SQLAlchemy for event logging

- Alert dashboard UI (HTML + Tailwind + JS)

- SMS/email notification on Level 3 (Twilio or SMTP)

Both — Shared

- GitHub setup, branching strategy, PR reviews, integration testing, documentation, and the final demo

2. Recommended Tech Stack

| Layer | Tool | Why |
| --- | --- | --- |
| Audio capture | PyAudio + SoundDevice | Standard Python mic streaming |
| Speech/keywords | Vosk (offline) | Works without internet; has Indian English model |
| Sound classification | YAMNet (via TensorFlow Hub) | Pre-trained for 521 sound classes |
| Backend/API | Flask | Lightweight, both familiar with Python |
| Real-time comms | Flask-SocketIO | Live push to dashboard without polling |
| Frontend | HTML + Tailwind + vanilla JS | Simple, no framework overhead |
| Database | SQLite + SQLAlchemy | Zero setup, local, perfect for prototype |
| Notifications | Twilio SMS / Gmail SMTP | Free tier is sufficient |
| Version control | Git + GitHub | Feature branch workflow |

3. System Architecture

🎙️ Mic → [Ananya] Audio Engine

├── Vosk keyword detection

├── YAMNet sound classification

└── Secret code counter

↓

[Ananya] Alert Classifier

→ maps to L1 / L2 / L3

↓

[Guru] Flask API (POST /alert)

→ writes to SQLite

→ emits SocketIO event

→ fires SMS/email on L3

↓

[Guru] Dashboard UI

→ live level indicator

→ event log table

→ system ON/OFF toggle

4. Alarm Level Specification

Level 1 — Low Alert Trigger: single threat keyword detected ("help", "fire", "robbery") Response: yellow indicator on dashboard, log entry, soft beep

Level 2 — Medium Alert Trigger: abnormal sound classified (scream, crash, gunshot) OR multiple keywords in a short window Response: orange indicator, prominent dashboard notification, repeated beep

Level 3 — High Emergency Trigger: secret voice code spoken 3× in succession, OR L1 + L2 within 30 seconds Response: red siren alert on dashboard, full-screen overlay, SMS/email dispatched, timestamped log

5. Week-by-Week Plan

Week 1 — Setup & Foundation

- Both: Create GitHub repo, set up branch structure (main, dev, feature/*), write README skeleton

- Both: Agree on the shared JSON alert event format (e.g. {type, keyword, level, timestamp}) and keywords.json config structure

- Ananya: Set up Python environment, install PyAudio + Vosk, verify mic capture works, build basic audio stream loop

- Guru: Flask app scaffold, SQLite schema (events table with id, type, level, keyword, timestamp), basic index.html stub

Week 2 — Core Detection Engine

- Ananya: Implement Vosk live keyword detection → test with threat word list

- Ananya: Integrate YAMNet for sound classification on audio chunks → test with scream/crash audio files

- Ananya: Build secret voice code tracker — count phrase repetitions within a sliding time window

- Guru: Build POST /alert and GET /events Flask endpoints; integrate Flask-SocketIO

- Guru: Wire frontend to SocketIO — live update alarm indicator and event log

Week 3 — Alerts, Alarms & Integration

- Ananya: Implement alarm level classifier with escalation rules and L1+L2 time-window logic

- Guru: Build the full dashboard UI — colour-coded alarm level cards, event log table, system toggle

- Guru: Integrate Twilio SMS or Gmail SMTP for Level 3 dispatch

- Both: End-to-end integration — wire audio engine → API → SocketIO → UI into one running system

- Both: Cross-review code via PRs; merge feature branches into dev

Week 4 — Testing, Polish & Demo

- Both: Full scenario testing — speak threat words, play alarm sound files, use secret voice code

- Ananya: Tune confidence thresholds; test edge cases (background noise, accents)

- Guru: Polish dashboard UI; build a Demo Mode that simulates alert events without needing the mic (critical for a clean presentation)

- Both: Write README with setup instructions + architecture diagram; record a short demo video

- Both: Final merge to main, tag v1.0, prepare live demo script

6. GitHub Workflow

Repository structure:

watzs/

├── audio_engine/        ← Ananya

│   ├── capture.py

│   ├── keyword_detector.py

│   ├── sound_classifier.py

│   ├── voice_code.py

│   └── alert_classifier.py

├── server/              ← Guru

│   ├── app.py

│   ├── models.py

│   ├── routes.py

│   └── notifier.py

├── frontend/

│   ├── index.html

│   └── dashboard.js

├── config/

│   └── keywords.json

├── tests/

├── requirements.txt

└── README.md

Branch naming:

- feature/ananya-keyword-detection

- feature/ananya-sound-classifier

- feature/guru-dashboard-ui

- feature/guru-flask-api

- feature/guru-sms-alerts

Rules: All feature branches → PR into dev. The other person reviews and approves. Only merge dev → main at end-of-week milestones.

Issue labels: ananya, guru, shared, bug — one Issue per feature task.

7. Risks & Mitigation

| Risk | Level | Fix |
| --- | --- | --- |
| Vosk accuracy poor with Indian accents | Medium | Use Vosk's vosk-model-en-in Indian English model |
| YAMNet false positives from background noise | High | Require 2 consecutive detections before triggering L2; add configurable confidence threshold |
| Integration issues between modules | Medium | Agree on JSON format Week 1; use mock data to test each module independently before wiring |
| Twilio billing/setup delays | Low | Use Gmail SMTP as primary fallback for notifications |
| Merge conflicts | Low | Clear folder ownership (Ananya = audio_engine/, Guru = server/ + frontend/) |

8. Final Deliverables Checklist

- ✅ Working prototype — runs on laptop, detects threats via mic in real-time

- ✅ Live alert dashboard — alarm level, event log, real-time SocketIO updates

- ✅ Secret voice code feature — demonstrable live

- ✅ Notification system — at minimum email on Level 3

- ✅ Demo Mode — simulates alerts without mic dependency (very important for the demo day)

- ✅ GitHub repo — clean commits, branches, Issues showing collaboration

- ✅ README — setup guide, architecture, feature list

- ✅ Demo video/recording — backup for submission

A few things worth flagging as you get started: the biggest technical risk is Vosk accuracy, so Ananya should test it with your actual voices and accents in Week 1 — if it's not working well, switch to Google's Speech Recognition API which is slightly easier to set up. Also, Demo Mode is something Guru should build by Week 3; it's a lifesaver if the mic misbehaves during the actual presentation. Finally, make sure you pin the keywords.json format before splitting up in Week 1 — it's the main interface between both your modules and aligning on it early will save a lot of back-and-forth.